## Patch List
f1r3node-rust: the path to a working branch with REV stacks (stall-loop design, revision 5)
Created 2026-10-29 against dev at 252a86d1d. Patch IDs and the two new branch names are proposed. Blue rows are branch markers (where a branch starts or is rebased); green rows are milestone markers (a pull request, a tag or a phase exit); orange rows open a phase. Grey italic rows are dropped. Yellow cells are for you to fill in.
# | Phase | Patch | Branch | Title | Content | Source | Main files | Depends on | Apply expectation | Exit evidence | Size | Status | PR number | Merged? (Yes/No)
PHASE 0 - Reduced Track A onto current dev (1 to 1.5 weeks). Its own pull request to dev.
BRANCH fix/stall-track-a-on-dev created from dev @ 252a86d1d (2026-10-28). Sources: fix/finality-stall-track-a @ 6deb949b6, fix/finalizer-forward-progress @ c36932d26, fix/stall-track-a-rest @ 0cb21310d.
1 | 0 | P0-00 | fix/stall-track-a-on-dev | Reconciliation list (no code) | Written list, reviewed before any code changes: for A1a, A4, A5 and A7, what dev already does, what Track A adds, what is kept and what is dropped. Also which clone-audit Tier 0 fixes dev already has. | dev 2edcb0bcc (oracle verdicts within a derivation, validated floor kept); 30453da91, 23dc2cd53, f1bc683d5 (pool snapshot reuse, mutex-free pool); bbfd6c00d (cone walk over cached block facts); a596e3eea, ecef0dd68, 2051b551a (buffer eviction, re-fetch cooldown) | - | - | n/a | Your review of the list | S | Not started
2 | 0 | P0-01 | fix/stall-track-a-on-dev | A2 Coalesce deploy-triggered proposals | Deploy-triggered proposals coalesce; they never mint empty blocks. | cherry-pick c93cff5ff | casper/src/rust/blocks/proposer/* | - | Clean | Proposer queue depth <= 1; existing A2 tests pass on dev | S | Ready
3 | 0 | P0-02 | fix/stall-track-a-on-dev | A8 DAG indices in memory | Latest messages and invalid blocks in memory; contains() without a representation; read-only equivocation access under the read lock. | cherry-pick 5d2f3aae2 | block-storage/src/rust/dag/block_dag_key_value_storage.rs | - | Clean | No full-table scan per block; block-storage tests | M | Ready
4 | 0 | P0-03 | fix/stall-track-a-on-dev | A6 Merge, replay and checkpoint off async workers | Replay, merge and checkpoint run in block_in_place. | cherry-pick 568773a3a | casper interpreter_util.rs, block processing | - | Clean | No consensus CPU work on tokio workers; casper tests | M | Ready
5 | 0 | P0-04 | fix/stall-track-a-on-dev | A1c part 1: atomic commit_lfb | commit_lfb validates under the write lock and writes metadata, commit marker and LFB pointer in one LMDB transaction; API path commits through the same check. | cherry-pick 86fd26ffe (with 634976db2 tests if separate) | block_dag_key_value_storage.rs, finalization_runner.rs | - | Clean; check against dev ec3e3ef4b (finalizer as the one LFB writer) | A commit is never partial; commit_lfb refusal tests | M | Ready
6 | 0 | P0-05 | fix/stall-track-a-on-dev | A1a Oracle progress across timed-out runs (reduced) | Keep only what dev lacks: the cache of facts about immutable blocks shared across runs and snapshots, and the immediate rerun after a timeout (at most three in a row). Dev already shares verdicts within one derivation and keeps the validated floor. | 8ba8b77f1, reduced per P0-00 | casper/src/rust/finality/*, finalization_runner.rs | P0-00 | Conflicts (dev 2edcb0bcc) | Cached and uncached derivations give the same floor across seven snapshots; timeout-rerun tests | S | Needs reconciliation
7 | 0 | P0-06 | fix/stall-track-a-on-dev | A1b Time only the derivation | The 15 s deadline covers the derivation only; the commit is never cancelled. | 5d78f252c | finalization_runner.rs | P0-04, P0-05 | Conflicts (dev d03621406, 3a455a679) | A timed-out run never commits; a commit is never cancelled | S | Needs port
8 | 0 | P0-07 | fix/stall-track-a-on-dev | A1c part 2: resumable floor cursor | FloorCursor with snapshot identity and reset-then-freeze policy; events publish after commit with a commit epoch, republished after a crash. | a6f9155bb | casper/src/rust/finality/*, finalization_runner.rs | P0-06 | Conflicts | Finalizer property tests; LFB never stalls in the soak | M | Needs port
9 | 0 | P0-08 | fix/stall-track-a-on-dev | A1 Finalizer forward-progress tests | The forward-progress test suite, adapted to dev's finalizer task structure. | 8b1b10f2a, plus coverage merged in #812 | casper/tests/* | P0-07 | Adapt | Tests pass on the branch | S | Needs port
10 | 0 | P0-09 | fix/stall-track-a-on-dev | A3 Pace proposals and cap the deploy pool | No user deploys in a proposal when floor distance > 128; pool refuses deploys above 64 x max-user-deploys-per-block with a retryable error (HTTP 503, Retry-After). | d1c3a970f | block_creator.rs, deploy pool, web API | P0-01 | Conflicts (block_creator.rs) | Floor distance bounded under burst load | S | Needs port
11 | 0 | P0-10 | fix/stall-track-a-on-dev | A4 One pool read per proposal (reduced) | Keep only what dev lacks after its snapshot reuse: each stored encoding verified once per process; pool cap checked under the insert lock. | 600689764, c4b8b40c4 (PoolSnapshot tests), reduced per P0-00 | block_creator.rs, deploy pool storage | P0-00, P0-09 | Conflicts (dev 30453da91, 23dc2cd53, f1bc683d5) | Prepare time flat in pool size | S | Needs reconciliation
12 | 0 | P0-11 | fix/stall-track-a-on-dev | A5 Batch the lifecycle register (reduced) | Lifecycle register batched per floor advance over cached block_facts, where dev's cone walk does not already cover it. | 1a928edc4, reduced per P0-00 | casper/src/rust/finality/deploy_lifecycle.rs | P0-00 | Conflicts (dev bbfd6c00d) | Observe time flat in open signatures | S | Needs reconciliation
13 | 0 | P0-12 | fix/stall-track-a-on-dev | A9 Cap the legacy rejection search | Per-group cap of 16 branches with deterministic greedy fallback, from rejection-search-cap-from-height; off by default. | 16c57af9c | casper merging (dag_merger.rs), configuration | - | Conflicts | Bounded merge time; default-off leaves behaviour unchanged | M | Needs port
14 | 0 | - | fix/stall-track-a-on-dev | A7 Buffer eviction and re-fetch cooldown | Dropped: dev has the equivalent (oldest-entry eviction and kept re-fetch cooldown, plus recoverable evicted blocks). | 46d49cb83 (not ported); dev a596e3eea, ecef0dd68, 2051b551a | - | - | - | - | - | Dropped
15 | 0 | - | fix/stall-track-a-on-dev | Track A supply-chain commits | Dropped: dev carries its own patched webpki and deny/policy state. | f2e8fb896, 05f2a3fa7, 155153ed4, 435e47554 (not ported) | - | - | - | - | - | Dropped
16 | 0 | P0-13 | fix/clone-audit-tier0 (separate) | Clone-audit Tier 0 fixes | Quadratic Env::put copying, quadratic replay scan, quadratic match fall-through, quadratic stream reassembly; port only those P0-00 finds missing on dev. Independent of cost accounting; separate small PR. | publications f1r3node-profiling/clone-audit.tex | rholang/src/rust/interpreter/* | P0-00 | New code | Microbenchmarks of the clone audit improve; full rholang tests pass | M | Check dev first
MILESTONE Phase 0 exit: stall and finalizer tests pass on the branch; prepush green. Open PR fix/stall-track-a-on-dev -> dev.
MILESTONE PR merged to dev. Record the merge commit as marker M0 (suggested tag: rev-stacks/m0-track-a).
PHASE 1 - The v6 seam on dev (1.5 to 2 weeks).
BRANCH feature/rev-stacks-ote created from fix/stall-track-a-on-dev tip (before the PR merges), then rebased onto dev at M0. Seam sources: feature/cost-accounted-ote @ 00e937882; integration/cost-accounted-ote-b1d866e45 @ d1f3ab5e1 (patches 0028 to 0035).
17 | 1 | P1-01 | feature/rev-stacks-ote | v6 module and hook points | The v6 order-then-execute module; the v6 flag and hook points in the proposer, validation and finalizer. | port cfc62b6ee, 8fff49669 (feature/cost-accounted-ote) | casper/src/rust/v6/*, casper.rs, finalization_runner.rs | M0 | Conflicts in 9 files (mostly constructor and test-harness signatures) | Crate builds; existing casper tests pass | M | Not started
18 | 1 | P1-02 | feature/rev-stacks-ote | Tranche 1 tests and docs | Three-validator test, format, documentation, coverage of v6 helpers and validity envelope-rejection branches. | port 5260aeda9, 456419895, e7469fd47, 320fc5e1a | casper/tests/*, test_node.rs, API tests | P1-01 | Adapt to dev harness | Three-validator v6 test passes | S | Not started
19 | 1 | P1-03 | feature/rev-stacks-ote | Protocol-6 genesis and ordered envelopes in bodies | Protocol-6 genesis and shard-wide mode switch; ordered envelopes in v6 bodies. Plain signed DeployData carrying phloLimit and phloPrice; no costacc types. | adapt 5b006ce52, 14e800d18 (integration branch) without the costacc dependencies | genesis, casper/src/rust/v6/*, models protobuf | P1-01 | Rewrite of costacc-coupled parts | v6 genesis builds; bodies round-trip | M | Not started
20 | 1 | P1-04 | feature/rev-stacks-ote | The executor on dev's meter | Concurrent runs from the block pre-state, one runtime session per envelope, dev's per-runtime phlo meter; merge in block order. Replaces rho_settlement.rs: no settlement contract and no system logs. Charging off (price 0 test shards) until phase 2. | adapt 98fb36d13, 4cb619605; delete rho_settlement.rs | casper/src/rust/v6/executor*, runtime manager | P1-03 | Rewrite of settlement-coupled parts | Execute and replay agree on a test shard | M | Not started
21 | 1 | P1-05 | feature/rev-stacks-ote | 0028 Contracts: records, evidence, validator sets, slashing | As delivered in patch 0028. | port 3500a5726 | casper/src/main/resources/*.rho, v6 | P1-04 | Expected light | Contract specs pass | S | Not started
22 | 1 | P1-06 | feature/rev-stacks-ote | 0029 Records and attestation in a protocol-6 body field | As delivered in patch 0029; record format without system logs. | port 8f10cbacc | models, casper/src/rust/v6/* | P1-05 | Expected light | Record and attestation tests | S | Not started
23 | 1 | P1-07 | feature/rev-stacks-ote | 0030 Persistent v6 executor state | As delivered in patch 0030. | port 44bde1f59 | casper/src/rust/v6/* | P1-06 | Expected light | Restart tests | S | Not started
24 | 1 | P1-08 | feature/rev-stacks-ote | 0031 Execution-lag gate | As delivered in patch 0031. | port 110452bf9 | block_creator.rs, v6 | P1-07 | Possible conflicts in block_creator.rs | Lag-gate tests | S | Not started
25 | 1 | P1-09 | feature/rev-stacks-ote | 0032 Deferred inclusion checks | As delivered in patch 0032. | port e6405030a | validation, v6 | P1-08 | Expected light | Inclusion-check tests | S | Not started
26 | 1 | P1-10 | feature/rev-stacks-ote | 0033 A-LIN policy from the protocol version | As delivered in patch 0033: alarm on legacy, halt on v6. | port 53f6723d2 | finalization_runner.rs, v6 | P1-09, P0-07 | Conflicts likely (finalizer) | A-LIN tests | S | Not started
27 | 1 | P1-11 | feature/rev-stacks-ote | 0034 Prune v6 executor state | As delivered in patch 0034. | port f3ab3ec68 | casper/src/rust/v6/* | P1-07 | Expected light | Pruning tests | S | Not started
28 | 1 | P1-12 | feature/rev-stacks-ote | 0035 Configuration, record packing and pacing | As delivered in patch 0035, without the vault-settlement record parts. | port d1f3ab5e1 | node configuration, v6 | P1-06 | Adapt | Configuration and packing tests | S | Not started
29 | 1 | P1-13 | feature/rev-stacks-ote | Offer status and receipts | Offered-deploy admission, bounded rejection log, retained records, BlockAPI::offered_status and the receipt route. | adapt 4b160089b, cdc23effd | casper API, node web routes | P1-04 | Adapt | Lifecycle and web tests | M | Not started
30 | 1 | P1-14 | feature/rev-stacks-ote | Phase 1 exit tests and cross-host fixture | Multi-validator ordering, execution, replay and attestation; cross-host replay fixture regenerated; measurement tests carried over (phase_timings_by_block_size, cost_breakdown_of_one_envelope). | adapt 05fde32d9 and the 0035a measurement tests | casper/tests/v6_* | P1-01 to P1-13 | Adapt | v6 blocks ordered, executed, replayed and attested on a test shard | S | Not started
MILESTONE Phase 1 exit. Rebase onto dev. Marker M1 (suggested tag: rev-stacks/m1-seam). Optional PR to dev here, or continue to phase 2.
PHASE 2 - Native REV (2 to 3 weeks). Q-18 (canonical settled form) must be answered before P2-05.
BRANCH feature/rev-stacks-ote continues from M1.
31 | 2 | P2-01 | feature/rev-stacks-ote | Located REV stacks: native primitives | Wallet channel computed from the owner's signature (public key, unforgeable name, compound signature); amount cells; deposits as separate datums; combine on spend. | new | rholang/src/rust/interpreter/accounting/*, rspace++ native ops | M1 | New code | Unit tests: deposits commute; spends from one wallet serialize | M | Not started
32 | 2 | P2-02 | feature/rev-stacks-ote | Genesis from wallets.txt | Genesis creates one located stack per wallets.txt line; records the genesis supply; no vault custody on v6 genesis. | new | casper genesis | P2-01 | New code | Genesis supply equals the sum of wallets.txt | S | Not started
33 | 2 | P2-03 | feature/rev-stacks-ote | Native transfer and the SystemVault facade | Transfer as one native debit and one native deposit; facade find returns the wallet channel, transfer is the native transfer. | new; SystemVaultV6.rho facade | casper/src/main/resources/*, accounting | P2-01 | New code | Transfer benchmark: < 12 ms per transfer; >= 150 transfers/s on 2 cores | M | Not started
34 | 2 | P2-04 | feature/rev-stacks-ote | The gate and the commitment table | Delta from phloLimit (until delta_sigma lands); native wallet read at the pre-state; commitment table C accumulated in block order; verdict and commitment in the record. Multi-signer funding refused until P3-02. | new | casper/src/rust/v6/gate* | P2-01 | New code | Gate property tests; sum of commitments never exceeds a balance | M | Not started
35 | 2 | P2-05 | feature/rev-stacks-ote | Per-COMM charging to the proposer, canonical form, box-car | Each COMM costs phloPrice REV from the paying wallet to F_sender(b). Canonical settled form: one combined datum per paying wallet, one deposit datum per envelope on the proposer channel; own-wallet reads see pre-state less commitment. Box-car size as a node configuration parameter. | new | reducer cost hook, v6 executor, node configuration | P2-04, Q-18 | New code | Replay equality across box-car sizes 1, 16, 1024 | M | Not started
36 | 2 | P2-06 | feature/rev-stacks-ote | Settlement and commitment release | Apply debits and deposit in canonical form, release C, exhaustion rule (full commitment to the proposer); kappa per wallet in the record. | new | v6 executor, records | P2-05 | New code | Funding microbenchmark < 8 ms for 1 to 4 wallets | S | Not started
37 | 2 | P2-07 | feature/rev-stacks-ote | Price floor and node price hook | Shard minimum price as a block-validity rule (from the genesis policy); validator acceptance price read through a price hook returning the node's configured fixed price. | new | validation, block_creator.rs, node configuration | P2-04 | New code | Below-floor block invalid; below-node-price deploy not included | S | Not started
38 | 2 | P2-08 | feature/rev-stacks-ote | REV hook and hook authority | No-op REV hook installed at genesis, called after each block's settlement (and epoch boundaries, per Q-20); genesis addresses and threshold; hook replacement requires a compound signature meeting the threshold. | new | genesis, casper/src/main/resources/* | P2-02, Q-19, Q-20 | New code | Unauthorised replacement refused; threshold replacement accepted | M | Not started
39 | 2 | P2-09 | feature/rev-stacks-ote | Conservation invariant | After each block, in play and replay, after the hooks: sum over wallets and validator channels equals the genesis supply. | new | v6 executor | P2-06, P2-08 | New code | Checked on every executor and benchmark run | S | Not started
40 | 2 | P2-10 | feature/rev-stacks-ote | Record arithmetic and the demand cap | Per-block demand cap D with 1.25 D + E r0 <= block-record-bytes; genesis check. 0035b dropped. | new | v6 records, genesis policy | P2-06 | New code | A 256-envelope block's record always fits | S | Not started
41 | 2 | P2-11 | feature/rev-stacks-ote | Remove the vault-based path | Remove applyPhloCost and its burn, the precharge and refund system deploys, vault reads in the gate, the cursors, holds, decide_groups, LaterHolds, the fee vault and the fixed fee, where removal is simpler than keeping them. | deletions | casper runtime manager, system deploys, SystemVault | P2-06 | Deletions | No vault call on the execution path | M | Not started
42 | 2 | P2-12 | feature/rev-stacks-ote | Client tooling | node deploy and the wallet query API on the new path; Embers and the gateway follow. | new | node CLI, web API | P2-03 | New code | End-to-end deploy and transfer from the CLI | S | Not started
43 | 2 | P2-13 | feature/rev-stacks-ote | Benchmarks and exit tests | Block benchmark (settlement < 5 % of block time, flat per envelope from 1 to 64, >= 150 one-sends/s on 2 cores); scaling run on 8 and 16 cores (eta >= 0.6). | adapt the carried-over measurement tests | casper/tests/v6_* | P2-01 to P2-12 | New tests | Targets met, or a measured explanation | S | Not started
MILESTONE Phase 2 exit: working branch with the core of the design. Rebase onto dev. Marker M2 (suggested tag: rev-stacks/m2-native-rev). PR feature/rev-stacks-ote -> dev.
PHASE 3 - Selective port from the integration branch (2 to 3 weeks, overlapping phase 2). Each item its own change.
BRANCH feature/rev-stacks-ote (or one short branch per item from M2). Source: integration/cost-accounted-ote-b1d866e45 @ d1f3ab5e1, frozen.
44 | 3 | P3-01 | feature/rev-stacks-ote | delta_sigma estimator | Tighter Delta from the linear proof instead of phloLimit; smaller commitments. | port rholang accounting/delta_sigma/* (b5f5406e0 and earlier B1/B2 commits) | rholang/src/rust/interpreter/accounting/delta_sigma/* | M2 | Port | Delta <= phloLimit on the corpus; gate tests | M | Not started
45 | 3 | P3-02 | feature/rev-stacks-ote | Per-signature metering | Charge each signature its own share; lifts the multi-signer refusal of P2-04. | port accounting/authority.rs and related | rholang accounting | P3-01 | Port | Multi-signer deploys charged exactly | M | Not started
46 | 3 | P3-03 | feature/rev-stacks-ote | Multi-signature wallets | Compound-signature wallets; spend in full or split explicitly. | port from the integration branch | accounting, casper | P3-02 | Port | Multi-signature wallet tests | S | Not started
47 | 3 | P3-04 | feature/rev-stacks-ote | Owners (DR-135) | Owners pay for stored-process regions from their own REV wallets at their own price; region refusal without REV. | port owner_offer.rs, e4c8d79d6 owner-funding core (REV parts only) | casper costacc owner modules | P3-02 | Port and trim | DR-135 owner tests on v6 | M | Not started
48 | 3 | P3-05 | feature/rev-stacks-ote | Sponsors and grants | Funding slots (unforgeable channels with deposited REV); grants with a validity window checked by the gate. | new on the funding-slot primitive | accounting, v6 gate | P2-04 | New code | Sponsored and granted deploy tests | S | Not started
49 | 3 | P3-06 | feature/rev-stacks-ote | Footprints for concurrency | Bernstein footprints for envelope independence and conflict decisions. | port from the integration branch | v6 executor | M2 | Port | Conflict tests; scaling run improves | M | Not started
MILESTONE Phase 3 exit: full scope. Rebase onto dev. Marker M3 (suggested tag: rev-stacks/m3-full). Final PR to dev.
FREEZE integration/cost-accounted-ote-b1d866e45 @ d1f3ab5e1 stays as a reference; not merged. P1 (vault precharge/refund in the work copy) is not shipped.
Counts
Patches (not dropped) |  |  | 47
Dropped |  |  | 2
Merged |  |  | 0

## Branches
Branches and markers (counts measured 2026-10-29 against dev @ 252a86d1d)
Branch | Role | Base / created from | Tip | Tip date | Behind dev | Ahead of dev | State | Action
dev | Merge target | - | 252a86d1d | 2026-10-28 | 0 | 0 | Live | Base for the new work. Rebase each phase onto it as the phase closes.
fix/finality-stall-track-a | Track A source (A1a, A2, A3) | older dev | 6deb949b6 | 2026-10-21 | 439 | 8 | Source | Cherry-pick into fix/stall-track-a-on-dev; retire after phase 0 merges.
fix/finalizer-forward-progress | Track A source (A1b, A1c) | fix/finality-stall-track-a | c36932d26 | 2026-10-21 | 583 | 13 | Source | As above.
fix/stall-track-a-rest | Track A source (A4 to A9) | fix/finalizer-forward-progress | 0cb21310d | 2026-10-21 | 583 | 19 | Source | As above. Its tip carries all of Track A.
feature/cost-accounted-ote | v6 seam, tranche 1 | older dev | 00e937882 | 2026-10-21 | 576 | 7 | Source | Port into feature/rev-stacks-ote (P1-01, P1-02); 9 conflicting files in the trial merge.
feature/cost-accounted-rho | Accounting research branch | older dev | 1b5a92f13 | 2026-10-27 | 128 | 531 | Reference | Source of delta_sigma, authority and owners via the integration branch (phase 3).
integration/cost-accounted-ote-b1d866e45 | Track B integration, patches to 0035 | dev b1d866e45 | d1f3ab5e1 | 2026-10-28 | 534 | 50 | Frozen reference | Do not merge. Source for phase 1 (0028 to 0035) and phase 3 ports.
fix/stall-track-a-on-dev (proposed) | Phase 0: reduced Track A | dev @ 252a86d1d |  |  |  |  | To create | PR to dev at phase 0 exit; marker M0 on merge.
feature/rev-stacks-ote (proposed) | Phases 1 to 3 | fix/stall-track-a-on-dev tip, rebased onto dev at M0 |  |  |  |  | To create | Markers M1, M2, M3; PR to dev at M2 (and M3).
fix/clone-audit-tier0 (proposed) | Interpreter defects | dev @ 252a86d1d |  |  |  |  | To create if needed | Only if P0-00 finds Tier 0 fixes missing on dev.
Markers
Marker | Meaning | Suggested tag | Commit (fill in) | Date (fill in)
Base | Where the new work starts | rev-stacks/base | 252a86d1d | 2026-10-28
M0 | Phase 0 merged to dev (reduced Track A) | rev-stacks/m0-track-a
M1 | Phase 1 exit: v6 seam on dev's base | rev-stacks/m1-seam
M2 | Phase 2 exit: working branch with native REV | rev-stacks/m2-native-rev
M3 | Phase 3 exit: full scope | rev-stacks/m3-full
Freeze | Integration branch frozen as a reference | - | d1f3ab5e1 | 2026-10-28

## Open Items
Open questions and proposed decisions (stall-loop design, revision 5)
Item | Question or decision | Blocks | State | Answer (fill in)
Q-18 | Confirm the canonical settled form: one combined datum per paying wallet and one deposit datum per envelope on the proposer channel; own-wallet reads see the pre-state balance less the commitment. | P2-05 | Open
Q-19 | Hook-update threshold: fixed k of n at genesis, or changeable by the hook authority itself. | P2-08 | Open
Q-20 | When the REV hook is called: after every block's settlement, at epoch boundaries, or both. | P2-08 | Open
Decision 9 | The canonical settled form (as Q-18). | P2-05 | Proposed
Decision 10 | Base: new branch from current dev with reduced Track A; integration branch frozen. | P0-00 | Proposed
Decision 11 | Phase 0 goes to dev as its own pull request. | M0 | Proposed
Decision 12 | The throughput targets become exit criteria (P2-13). | M2 | Proposed
Decision 13 | Clone-audit Tier 0 fixes land on dev beside phase 0. | P0-13 | Proposed
Names | Branch names fix/stall-track-a-on-dev and feature/rev-stacks-ote, and the rev-stacks/* tags. | P0-01 | Proposed